## Backlog
BE/FE | Giai đoạn | Task ID | Tên Task | Việc cụ thể | Phụ thuộc (Depends on) | Event publish | Ghi chú
BE1 | 1 | T01 | Repository / Docker / Shared Backend Foundation | Solution structure; common response wrapper; exception middleware; correlation ID; logging; validation base; Dockerfiles/Compose; SQL Server; RabbitMQ; object storage | T00 | - | BE1 lead phần backend foundation; FE1 làm mobile shell song song
BE1 | 1 | T02 | Identity, JWT & Role-aware Shell | User, Role entity; Login/Refresh/Logout/Me; password hashing; JWT; authorization policy theo role; Gateway JWT validation + routing ban đầu | T01 | - | Critical path
BE1 | 1 | T03 | Customer Profile & Horse Management | Customer profile; Horse CRUD; ownership validation; horse status; passport/registration fields | T02 | -
BE1 | 1 | T04 | Create Transport Request | Request draft/detail; add/remove horses; origin-destination; schedule; requirements; validation; save draft | T03 | -
BE1 | 1 | T05 | Submit Request & Manager Approval | Submit; manager queue; request-information/approve/reject + reason + audit; tạo TransportOrder transactionally, chống tạo trùng | T04, T02 | Booking.RequestApproved, Booking.OrderCreated | Điểm nghẽn chính - ưu tiên đẩy nhanh
BE1 | 2 | T12 | Trip Execution & Checkpoint Timeline | Trip events: departure, checkpoint arrival/departure, customs cleared, quarantine milestone, destination arrival; timeline | T11 (BE3) | - | Chờ BE3 xong T11 mới mở khóa
BE1 | 2 | T13 | GPS Tracking & ETA | GPS point ingestion; current location; lịch sử vị trí; ETA calculation/service | T12 | -
BE1 | 2 | T14 | Horse Health Monitoring | Health log: condition, stress level, observation, ảnh; health alert | T12 | Tracking.HealthAlertRaised
BE1 | 3 | T21 (phần BE1) | Integration & E2E Hardening | Integration test; consumer idempotency; retry/DLQ; concurrency handling; API contract checks cho Identity/Booking/Tracking | T01-T20 liên quan | - | T21 là trách nhiệm chung; mỗi BE hardening service mình sở hữu
BE2 | 1 | T06 | Compliance Master Data & Regulation | Countries/reference; document types; regulation rules; required-document mapping; quarantine/customs/inspection requirement | T02 | - | Chạy song song với BE1 T03-T05
BE2 | 1 | T07 | Horse / Trip Documents | Upload document; file storage; metadata; list theo horse/request/trip; review history; approve/reject/request-info; expiry validation | T05 (BE1), T06 | - | Tích hợp thật chờ T05
BE2 | 1 | T08 | Clearance & Compliance Readiness | Clearance case; case documents; submission/review states; required-document calculation; readiness result | T07, T06, T05 | Compliance.ClearanceApproved, Compliance.ComplianceReady | Critical path để mở T11
BE2 | 2 | T15 | Incident Management | Incident creation; severity; attachments; status; resolution; notification event khi nghiêm trọng | T12, T14 (BE1) | - | Chờ Trip/Health data thật
BE2 | 3 | T19 | Notification Center & Push | Notification service; device tokens; unread/read; event consumers; audience routing; payload/deep-link metadata | T05, T08, T12, T15, T16, T17 | - | Owner notification backend
BE2 | 3 | T18 | Cost / Revenue / KPI Dashboard | Cost items; revenue items; on-time delivery; average delay; trip duration; vehicle utilization; incident rate; compliance delay | T10, T12, T17 | - | Đọc dữ liệu nhiều service - làm cuối
BE2 | 3 | T21 (phần BE2) | Integration & E2E Hardening | Integration test; consumer idempotency; retry/DLQ; concurrency handling; API contract checks cho Compliance/Incident/Notification/Reporting | T01-T20 liên quan | - | T21 là trách nhiệm chung
BE3 | 1 | T09 | Fleet & Location Master Data | Country, Location; Vehicle, Stall; Airline, Flight Booking; availability checks | T02 | - | Chạy song song với BE2
BE3 | 1 | T10 | Trip & Route Planning | Tạo Trip từ Order đã duyệt; RoutePlan/Version; RouteLeg; Checkpoint; submit/approve/activate route; resource assignment | T05 (BE1), T09 | - | Tích hợp thật chờ T05
BE3 | 1 | T11 | Trip Readiness & Pre-departure | Readiness = active route + resource/staff/horse-stall assignment + compliance ready; publish TripReady | T08 (BE2), T10 | Planning.TripReady | Điểm nghẽn thứ 2 - mở khóa T12
BE3 | 2 | T17 | Handover & Acceptance | Handover; per-horse inspection; accept/dispute; signature; attachments; completion validation | T12 (BE1) | Handover.HandoverCompleted
BE3 | 3 | T16 | Emergency Route Change | Proposed RoutePlanVersion; RouteChangeRequest; delay estimate; additional cost; approve/reject/apply; archive old version | T10, T15 (BE2) | Planning.RouteChangeApplied
BE3 | 3 | T20 | Audit & Operational History | Audit approval/rejection; document review; route activation/change; incident resolution; handover completion | T05 trở đi | - | Đọc dữ liệu nhiều service - làm cuối
BE3 | 3 | T21 (phần BE3) | Integration & E2E Hardening | Integration test; consumer idempotency; retry/DLQ; concurrency handling; API contract checks cho Planning/Handover/Audit | T01-T20 liên quan | - | T21 là trách nhiệm chung
BE3 | 3 | T22 | Production Docker & Deployment | Production Dockerfiles; env/secrets; reverse proxy/ingress; health checks; DB migration; RabbitMQ/object storage config; logging/monitoring | T21 | - | BE3 lead deployment; BE1/BE2 hỗ trợ service mình sở hữu
FE1 | 1 | T01 | Mobile Foundation / App Shell | React Native project; TypeScript config; navigation shell; theme/design tokens; API client skeleton; TanStack Query provider; common loading/error/empty components | T00 | - | Dựng mock + app shell ngay từ đầu
FE1 | 1 | T02 | Login & Role-aware Navigation | Login; splash/session restore; secure token storage; refresh flow; logout; authenticated/unauthenticated navigation; role-based navigator | T01 | - | Chốt auth contract sớm với BE1
FE1 | 1 | T03 | Profile & Horse Management UI | Profile; Horse list/detail; Add/Edit horse; form validation; ownership/permission states | T02 | -
FE1 | 1 | T04 | Transport Request UI | Request list; Create Request wizard/form; select horses; route/schedule input; special requirements; save/reopen draft | T03 | -
FE1 | 1 | T05 | Request Submit & Manager Approval UI | Customer submit confirmation/status/returned-info; Manager queue/detail; approve/reject/request-info dialogs | T04, T02 | - | Critical path FE
FE1 | 1 | T06 | Compliance Master Data UI | Document Type list/detail; Regulation list/editor; required document editor | T02 | - | Có thể xen kẽ khi chờ BE1
FE1 | 1 | T09 | Fleet & Location Master Data UI | Vehicle/stall/location/flight booking list & detail; CRUD forms; availability states | T02 | - | Có thể xen kẽ với T06
FE1 | 1 | T07 | Horse / Trip Documents UI | Horse documents; upload; document status; specialist review queue/detail; approve/reject/request-info | T05, T06 | -
FE1 | 1 | T08 | Compliance Readiness UI | Clearance list/detail; readiness dashboard; missing/expired document display; blocker states | T07, T06, T05 | -
FE1 | 1 | T10 | Trip & Route Planning UI | Trip list/detail; route editor; checkpoint editor; resource assignment screens | T05, T09 | - | Làm contract-first với BE3
FE1 | 1 | T11 | Trip Readiness UI | Readiness checklist; blockers; ready/not-ready state; coordinator/manager confirmation | T08, T10 | - | Critical path mở T12
FE1 | 2 | T12 | Trip Execution & Timeline UI | Driver active trip; next checkpoint; milestone update; checkpoint update; customer trip timeline | T11 | -
FE1 | 2 | T14 | Horse Health Monitoring UI | Active-trip horse list; health form; image upload; health history; customer/manager health status | T12 | -
FE1 | 2 | T13 | GPS Tracking & ETA UI | Map/tracking; current position; route context; ETA; stale/offline and last-update state | T12 | - | Có thể làm song song T14
FE1 | 2 | T17 | Handover & Acceptance UI | Handover preparation; horse acceptance; inspection review; signature; accept/dispute; completion screen | T12 | -
FE1 | 2 | T15 | Incident Management UI | Driver create incident/attach image/active incidents; manager/coordinator queue/detail/resolve/close | T12, T14 | -
FE1 | 3 | T16 | Emergency Route Change UI | Coordinator propose/compare old-new route; Manager approve/reject; Driver active route update; Customer updated ETA/status | T10, T15 | -
FE1 | 3 | T19 | Notification Center & Push UI | Notification center; unread/read; push permission/token registration; deep links về đúng feature screen | T05, T08, T12, T15, T16, T17 | -
FE1 | 3 | T18 | Manager KPI Dashboard UI | Revenue; cost; completed trips; delays; on-time rate; active trips; incidents; loading/filter/empty states | T10, T12, T17 | -
FE1 | 3 | T20 | Audit Viewer UI | Manager/Admin audit viewer; filters; actor/time/reason; old/new state/detail view | T05 trở đi | -
FE1 | 3 | T21 | FE Integration & E2E Hardening | Offline/error handling; stale state; navigation edge cases; token expiration; end-to-end critical-flow smoke tests | T01-T20 | - | Hardening toàn app
FE1 | 3 | T22 (hỗ trợ FE) | Production Build & Release Support | Production API/env configuration; Android/iOS release build config; build smoke test; verify health/API connectivity in deployed environment | T21 | - | Hỗ trợ BE3, không phải owner deployment

## Chú thích
Chú thích / Legend
Màu BE/FE | Ý nghĩa
Xanh dương nhạt (BE1) | Platform + Identity + Booking → Tracking
Cam nhạt (BE2) | Compliance → Incident → Notification / Dashboard
Xanh lá nhạt (BE3) | Planning → Handover → Route Change / Audit / Deployment
Tím nhạt (FE1) | React Native toàn bộ app; làm contract-first theo critical path
Màu Giai đoạn | Ý nghĩa
Giai đoạn 1 (xanh dương nhạt hơn) | Foundation + luồng nghiệp vụ trước departure
Giai đoạn 2 (cam nhạt) | Trip execution / health / incident / handover
Giai đoạn 3 (xanh lá nhạt) | Cross-service, dashboard, notification, audit, hardening, deployment
Lưu ý chung
1 FE duy nhất | Ưu tiên critical path; T06/T09 có thể xen kẽ khi chờ; không cần đợi backend code xong nếu OpenAPI/response mẫu đã chốt
Contract-first | Mỗi BE chốt OpenAPI + request/response mẫu trước khi code thật để FE làm với mock ngay
T21 | Cả 3 BE hardening service mình sở hữu; FE hardening toàn app
BE rảnh | Nhảy phụ BE khác đang ở critical path, không ngồi chờ dependency